## Introduction and How to use
GOLD STANDARD FOR SUSTAINABLE URBAN DEVELOPMENT
Version 0.2
Annex D - GOVERNANCE AND MANAGEMENT SYSTEMS
Introduction to the tool | Interventions applying for certiifcation are required to demonstrate that there are Governance, Management systems (GMS) in place to ensure smooth management and implementation of the urban intervention. Developers must also demonstrate that capacity needs of stakeholders are considered and steps are taken to ensure that the necessary capacity building measures are taken. The requirements are laid down in the form of a series of indicators/criteria that must be used for self-assessment by the developer. These criteria also include levels of development which are aimed to help the developer achieve continuous improvement on these aspects. The self-assessment/reporting on these criteria are subject to third-party verification to ensure that there is a continuous improvement achieved by the developer. In cases where sub-contractors (e.g. Climate Change consultants) are engaged in an intervention/programme, the experience of such sub-contractors can be used by the intervention developer to assess the level of development for criteria in this tool as long as this experience can be demonstrated to be relevant.
How to use this tool | This tool can be used for both ex-ante and ex-post assessment of urban interventions. An ex-ante assessment can occur during or after implementation of an intervention. It is helpful to evaluate the likelihood that the intervention will deliver the objectives, and to assess the environmental integrity and related risks. An ex-post assessment of an intervention occurs prior to achievement of the objectives but ideally some degree of institutional implementation has already taken place and design is not limited to only documentation. It is helpful to measure the achievements and extent to which the intervention met its goals, and will assess the processes in place to ensure that future deliverables are met. Depending on the status of implementation of the urban intervention, the tool can be used in ex-ante and ex-post contexts.
Developers shall follow the following broad steps in using this tool -
Step 1: Developers shall define Governance, Management and Capacity building system at the programme (a series of interventions) level. The assessment of the pre-defined criteria listed in the tab "Criteria" of this tool will be carried out at Programme level and not individual intervention level.
Step 2: Developers are required to self-assess the given indicators / criteria, where applicable and determine if the level of development is 'High', 'Medium' or 'Non compliance'. If the indicator/criteria is not applicable, it shall be justified. An independent third party will audit the developer's self-assessment.
Step 3: Developers shall update their self-assessment annually. An improvement in the level of development is required to be demonstrated over the course of the crediting period.

## Criteria
GOLD STANDARD FOR SUSTAINABLE URBAN DEVELOPMENT
Version 0.2
Assessment area, criteria/indicators and Level of Development
| Assessment Area | Criteria/Indicators | Level of Development
MODULE 1 - Mitigation Project/Programme This module aims to assess the relative robustness of the mitigation Project’s design and implementation. At the design stage, this module evaluates the mitigation Projects’ objectives and targets, and alignment with national policies and priorities. It also assesses the planning of the program to evaluate the level of risk involved in its implementation and the proposed investment structure and planning. At the implementation stage, this module evaluates the results that have been achieved, the monitoring and reporting of emissions, and how corrections are handled when the results deviate from their established objectives and targets.
| Objectives and Targets (The objectives of the project should be defined, contribute to climate change mitigation, and be aligned with the jurisdiction’s priorities. Targets should also be quantified, taking into account a well-defined baseline, and be well justified.) | Alignment of the Project objectives and the jurisdictional priorities on Climate Change | High | The Project design documentation justifies the alignment of the Project’s objectives with the jurisdiction priorities on climate change and to the extend applicable the jurisdiction low emissions development strategy (LEDS) and sectorial policies and regulations applicable to the geographical scope of the program.
|  |  | Medium | The Project objectives respond to the needs of specific stakeholders (sector, sub national governments, markets, etc.) but it is not evidenced of the alignment of the Project’s objectives with the Jurisdiction objectives and targets towards climate change mitigation. | -
|  |  | No compliance | There is no evidence of the contribution of the Project objectives to achieve relevant jurisdictional strategies and policies. | -
|  | Developer targets for climate change mitigation | High | The Project targets take into account it's baseline emissions and mitigation scenarios. The targets are quantified and based on, among others, a cost benefit analysis of the potential achievement through the Project in different emission sources, its technological options, its financial, sectorial development goals and business requirements, and the views of interested parties.
|  |  | Medium | The Project has specific quantified mitigation targets based on the baseline assessment but there is no evidence on how the different Projects planned are selected taking these targets into account
|  |  | No compliance | The Project includes general objectives for mitigation but not specific quantified targets.
| Planning (Developers should assess the extent to which their plan has been designed and implemented to achieve the Project’s objectives and targets. Plans should include a number of key elements, such as financing requirements and a description of each of the envisaged individual Projects.) | Project planning to achieve established targets | High | The Project has defined and formally approve plan(s) for achieving its objectives and targets. The Plan(s) includes designation of responsibility for achieving objectives and targets at relevant functions and levels of the Project developer.
|  |  | Medium | The Project establishes, implement, and maintain a plan(s) for achieving its objectives and targets. The plan(s) does not clearly include designation of responsibility for achieving objectives and targets at relevant functions and level of the Project developer.
|  |  | No compliance | The Project doesn't establish, implement, nor maintain a plan(s) for achieving its objectives and targets
|  | Portfolio of Projects for the Programme implementation (This criteria will be relevant in case of a portfolio of Projects implemented as part of a Programme) | High | The achievement of the programme’s Objectives and Targets is planned through the implementation of a portfolio of Projects (policies and/or Projects) over a defined time period. The portfolio's components are clearly defined and it represents a combination of cost effective implementable actions, which can contribute to achieve the level of commitment of the Project.
|  |  | Medium | The programme includes a general Implementation Plan but it is not clearly defined which are the Projects proposed and its scope and objectives.
|  |  | No compliance | The programme does not include a defined Implementation Plan
|  | Risk analysis for implementation, risk management and mitigation plan | High | The Project clearly identifies the risks for implementation of the selected Projects and has designed a risk mitigation plan including the structure within the Project developer to identify (including frequency), prioritize and mitigate the risk (s). The Project documents include a process for periodically updating this risk analysis.
|  |  | Medium | The Project identifies all the potential risks for implementation but no action is planned to minimize the probability of those risks to happen or the actions proposed are not considered sufficient. There is no structure within the Project developer to identify, prioritize and mitigate the risk (s)
|  |  | No compliance | The Project does not identify the potential risks for implementation of the selected Projects.
|  | Investment Planning | High | The Project design includes an evaluation of the investment requirements and possible investment structures. It includes a realistic investment plan based on justified and conservative assumptions.
|  |  | Medium | There is an investment plan developed but it is not totally transparent on the assumptions used or modelled outputs.
|  |  | No compliance | There is no investment plan; or the existing investment plan is likely to be unrealistic.
|  | Project compliance with regulatory requirements | High | The Project processes include the evaluation of regulatory and legal compliance of the Projects proposed under the program, including when applicable, environmental impact assessments. The processes are implemented.
|  |  | Medium | The process exists but there is no evidence of its application to ongoing Projects.
|  |  | No compliance | Regulatory and legal compliance has not been taken into account.
|  | Resources available for implementation | High | The Project developer has documented commitment to ensure the availability of resources essential to establish, implement and sustain the Project. Resources including human resources with specialized skills, training and capacitation of existing staff, organizational infrastructure, technology and financial resources. Resources are available also for the Project developer and for implementation of GHG estimate and Monitoring activities.
|  |  | Medium | The Project developer is committed to ensure the availability of resources essential to establish, implement, and sustain the Project. Existing resources only cover part of the needs and there is no clear pathway to ensure the availability of resources for the rest of the implementation process or the certainty of future funding is limited.
|  |  | No compliance | There is no certainty as to the availability of resources essential to establish, implement, sustain and improve the Project.
| Roles, Responsibilities and Authorities (Identification of the roles, responsibilities, and authorities of all entitties involved in the project needed to ensure successful implementation of the Project including the definition of the entities best suited for each role and responsibility is critical. This will help ensure that the necessary resources are available.) | Definition of roles, responsibilities and level of authority for Project design and implementation | High | The Project developer clearly defines and document roles, responsibilities and level of authority/decision-making within its scope and boundaries; it has also defined the communication paths in order to facilitate effective management.
|  |  | Medium | The Project developer clearly defines and document roles, responsibilities and level of authority/decision-making within its scope and boundaries; but it doesn‘t define the communication channels to facilitate an effective management.
|  |  | No compliance | Roles, responsibilities and authorities are not defined, documented or properly communicated.
| Documents, document control and records (Documentation procedures and systems are required to effectively manage the program and its components. There should also be an emissions reduction tracking system. The documentation that should be compiled and archived should also be listed.) | Project operation and management documented system | High | The Project Developer has established and is operating a management system, which includes (if appropriate) documented procedures for the implementation of the Project. The management system is aligned with the PDAC (Plan, Do, Check, Act cycle) and is both auditable and verifiable
|  |  | Medium | The Project developer has established a management system for the implementation of the Project, but it does not cover all areas of management required to ensure proper functioning.
|  |  | No compliance | The Project has not implemented a management system.
| Monitoring and Reporting (These indicators should assesses the extent to which an MRV action plan is adequately designed and implemented, including key performance indicators, GHG monitoring and reporting systems, third party periodic audits, and disclosure of results.) | The Project Key performance indicators process | High | There is a defined process to identify, implement and periodically evaluate key performance indicators to demonstrate that the Project results are in line with its objectives and targets, including oversight of: - Planning and implementation, Financial and Investment, Emission reductions, Sources and sinks and other identified sustainable development benefits. Actions are taken to correct any deviation
|  |  | Medium | Key indicators identify but no evidence of its periodic evaluation or the key indicators do not cover all aspects of the Project objectives and targets.
|  |  | No compliance | Key indicators have not been defined.
Module 2 - Project/programme developer This module rates the track record and capacity of the Project developer to design and implement the mitigation program. It covers its investment management capabilities, technical expertise,and the assessment of the management system of the developer.
| Management Framework | Relevant stakeholders and Monitoring & Reporting (MR) supporting agencies identified | High | The entity/es in charge of the design and implementation of the Project is clearly specified. A comprehensive list of all relevant stakeholders and measurements and reporting (MR) supporting agencies, if any, for conducting the GHG estimate and MR activities is provided.
|  |  | Medium | There is ambiguity or inconsistency across the documentation about the Project developer. Some of the stakeholders and MR supporting entities are listed, but there are relevant ones for GHG estimate and MR activities that are omitted or not identified yet.
|  |  | No compliance | Neither the Project developer, nor the relevant stakeholders and MR supporting agencies are specified.
|  | Roles, responsibilities, authorities and accountability within the Project developer | High | The Project developer has a documented and approved framework of roles, responsibilities and authorities clearly defined and followed to implement the Project. Responsibilities and authorities to reach the established sustainable development goals are clearly defined and implemented. This includes mechanisms to allocate responsibilities to entities within and outside the Project developer when appropriate. The Project includes a plan for holding different parties accountable in case of the sustainable objectives are not implemented or achieved and the consequences of it.
|  |  | Medium | There are some roles, responsibilities and authorities recognized within the Project Developer but not all along the organizational structure; or although they are clearly defined, not all have been implemented. Responsibilities and authorities have been defined but there is no evidence of their implementation over time. The Project includes a plan for holding different parties accountable in case of the sustainable objectives are not implemented or achieved but there are no consequences described.
|  |  | No compliance | Roles, responsibilities and authorities within the Project developer are not clearly defined. Responsibilities and level of authority to ensure the success in the achievement of the proposed development goals are not defined. Vague reference to accountability.
|  | Coordination between the Project Developer and the entities responsible for MR | High | There are rules and processes in place for the entities responsible for MR to coordinate and report back to the Project developer
|  |  | Medium | There are some vague rules or processes to ensure coordination between the Project developer and the entities responsible for MR
|  |  | No compliance | There are no rules or processes to ensure coordination between the Project developer and the entities responsible for MR
|  | The Project developer Management System | High | The Project Developer has an implemented Management System audited by a third party entity
|  |  | Medium | There is evidence of the existence and implementation of a Management System but it is not audited by a third party entity
|  |  | No compliance | The Project Developer has not implemented a Management System at all
|  | Emergency preparedness and response | High | The Project has established and maintained procedures - • to identify potential accident and emergency situations • to respond to these situations should they arise and • for preventing and mitigating the environmental impacts that may be associated with them The Project developer periodically tests these procedures where practicable and review and revise them where necessary - particularly after the occurrence of accidents or emergency situations. The Project has established and maintained procedures - • to identify potential accident and emergency situations • to respond to these situations should they arise and • for preventing and mitigating the environmental impacts that may be associated with them The Project developer periodically tests these procedures where practicable and review and revise them where necessary - particularly after the occurrence of accidents or emergency situations.
|  |  | Medium | The Project has established and maintained procedures - • to identify potential accident and emergency situations • to respond to these situations should they arise and • for preventing and mitigating the environmental impacts that may be associated with them The Project developer does not periodically tests these procedures where practicable and does not review and revise them
|  |  | No compliance | The Project has not established any procedures
| Financial management (The Project design should include methodologies to report and provide transparency on the financial flows of the Project and, where relevant, of experience with internationally financed programs.) | Methodologies to reporting and transparency of financial flows received and used, including actual disbursement, etc. | High | The Project Developer has methodologies to reporting and transparency of financial flows received and used to date (including actual disbursement) and complies with them
|  |  | Medium | The Project Developer has methodologies to reporting and transparency of financial flows but does not comply with them
|  |  | No compliance | The Project Developer doesn't have methodologies to reporting and transparency of financial flows.
|  | Past experience in the management and implementation of externally financed programs | High | The Project Developer has a wide and recognized experience in the management and implementation of internationally financed programs
|  |  | Medium | The Project Developer has some experience in the management and implementation of internationally financed programs but is still strengthening its capabilities
|  |  | No compliance | The Project Developer has no experience in the implementation of externally internationally financed programs
|  | Climate Change related experience | High | The Project developer has a specific area devoted to Climate Change Programs and there is evidence of historical performance improvement and active present participation in CC programs and initiatives.
|  |  | Medium | The Project developer has a specific area devoted to Climate Change Programs but there is no evidence of historical performance improvement and active participation in CC programs and initiatives.
|  |  | No compliance | The Project developer has an area devoted to general environmental / sustainable subjects but with no specific Climate Change experience.
|  | The Project developer technical capability | High | The Project Developer has a documented process in place to be able to identify best practices and apply this- upkeep and oversight as to the appropriate use of appropriate methodologies, their latest versions, needs of MRV vs. baseline scenarios, etc.
|  |  | Medium | There is evidence of the adoption of methodologies and/or standards but there is no process in place to align them with best practices.
|  |  | No compliance | The Project Developer has not a documented process in place to be able to identify best practices and there is no evidence either of the adoption of methodologies and/or standards
| Capacity Building | Training, awareness and competence | High | All staff who work in the operation of the Project receive the appropriate training. The Project makes them aware of: • the importance of conformance with the requirements of the Project • the significant impacts of their work activities and the benefits of improved personal performance • their roles and responsibilities in the successful functioning of the the Project Staff performing tasks which can cause significant environmental/social/economic impacts are deemed competent to do so. (Competence is assessed on the basis on their education, training and/or experience.)
|  |  | Medium | All staff who work in the operation of the Project receive the appropriate training. It is not known if the Project makes them aware of: • the importance of conformance with the requirements of the Project • the significant impacts of their work activities and the benefits of improved personal performance • their roles and responsibilities in the successful functioning of the the Project Staff performing tasks which can cause significant environmental/social/economic impacts are deemed competent to do so. (Competence is assessed on the basis on their education, training and/or experience.)
|  |  | No compliance | Staff working in the operation of the Project do not receive appropriate training
|  | Identification and capacity builidng of other relevant stakeholders | High | The Project developer has identified capacity building needs of relevant stakeholders other than those who are directly engaged in the implementation of the Project (e.g. staff operating the Project as above) and ensured that the capacity building measures are implemented. As a bare minimum, the following stakeholder categories shall be covered - a. Municipal and other local organisations associated with the Project to play a greater role in the Project implementation b. Broader stakeholders peripheral to the project.
|  |  | Medium | The Project developer has identified capacity building needs of relevant stakeholders other than those who are directly engaged in the implementation of the Project (e.g. staff operating the Project as above) and capacity building measures are planned to be implemented. As a bare minimum, the following stakeholder categories are also covered - a. Municipal and other local organisations associated with the project to play a greater role in the Project implementation b. Broader stakeholders peripheral to the Project.
|  |  | No compliance | Other relevant stakeholders are not identified.